## 现状
POV3D 显性目的进度看板 — 2026-10-13 (当前期 V0；状态按「最新硬件实测 vs 当前期目标」自动判定，krs.csv 人工状态列可覆盖)
目的 | 显性目的 | 实现途径 | 目的状态 | KR | 指标 | 单位 | 方向 | 最新实测 | 实测日期 | 阶段 | V0 目标 | V1 目标 | V2 目标 | KR 状态 | 最新来源 | 距 V2 达成
1 | 画面能实时变化 | 数据通路 | ✅ 达成当前期目标 | KR1.1 | 内容刷新率 (假转, 管线能力) | fps | 越大越好 | 15 | 2026-10-13 | V0 2047 | 15 | 12 | 15 | ✅ | dr1v90 596b191 / 9bf16ad | 100%
|  |  |  | KR1.2 | 端到端延迟 p50 | ms | 越小越好 | 95 | 2026-10-13 | V0 2047 | 100 | 70 | 70 | ✅ | dr1v90 9bf16ad | 73.68%
|  |  |  | KR1.7 | 端到端延迟抖动 p99 | ms | 越小越好 | 236.6 | 2026-10-13 | V0 2047 | 250 | 120 | 120 | ✅ | dr1v90 9bf16ad | 50.72%
|  |  |  | KR1.3 | WiFi 可用带宽 | Mbit/s | 越大越好 | 160 | 2026-10-12 | V0 2047 | 10 | 62 | 62 | ✅ | claude_memory/project_m90_wifi_p2p_1012.md | 100%
|  |  |  | KR1.4 | 主机出帧耗时 p99 | ms | 越小越好 | 22 | 2026-10-13 | V0 2047 | 50 | 50 | 50 | ✅ | dr1v90 9bf16ad | 100%
|  |  |  | KR1.5 | 板上切片耗时 (每帧) | ms | 越小越好 | 17.3 | 2026-10-13 | V0 2047 | 55 |  |  | ✅ | dr1v90 596b191
|  |  |  | KR1.6 | 内容刷新率 (实转上屏) | fps | 越大越好 | 10.8 | 2026-10-12 | V0 2047 | 10.8 | 12 | 15 | ✅ | claude_memory/project_slice_3bit_cpu_trial.md (D9 首次转起来 640–654 RPM) | 72%
2 | 体帧率达到 30 Hz | 显示优化 | ✅ 达成当前期目标 | KR2.1 | 体帧率 | Hz | 越大越好 | 21.7 | 2026-10-12 | V0 2047 | 21.7 | 24 | 30 | ✅ | claude_memory/project_slice_3bit_cpu_trial.md | 72.33%
3 | 画面更清晰 | 显示优化 | ✅ 达成当前期目标 | KR3.1 | 每面像素数 | px | 越大越好 | 28800 | 2026-10-12 | V0 2047 | 28800 | 28800 | 41472 | ✅ | claude_memory/project_slice_3bit_cpu_trial.md | 69.44%
|  |  |  | KR3.2 | 每圈片数 | 片 | 越大越好 | 142 | 2026-10-12 | V0 2047 | 142 | 358 | 605 | ✅ | claude_memory/project_slice_3bit_cpu_trial.md | 23.47%
4 | 颜色更丰富 | 显示优化 | ⏸ 无数据 / 未开始 | KR4.1 | 色深 | bit/通道 | 越大越好 | 3 | 2026-10-12 | V0 2047 | 3 | 12 | 12 | ✅ | claude_memory/project_slice_3bit_cpu_trial.md | 25%
|  |  |  | KR4.2 | 链路色深 12-bit 已验证 (1=是) | 是/否 | 越大越好 | 1 | 2026-10-13 | 仿真 | 1 | 1 | 1 | ⏸ | dr1v90 cdf49c6 (gw5a_bridge/p1 verify ALL PASS) | 100%
5 | 立体像不变形、两面对齐、无重影 | 几何 | 🔄 进行中 / 未达标 | KR5.1 | 几何 LUT 复现正确 (1=逐字节复现) | 是/否 | 越大越好 | 1 | 2026-10-13 | V0 2047 | 1 | 1 | 1 | ✅ | dr1v90 44ed2cd | 100%
|  |  |  | KR5.2 | 左右镜像已核实 (1=已核) | 是/否 | 越大越好 | 0 | 2026-10-13 | V0 2047 | 1 | 1 | 1 | 🔄 | claude_memory/project_short_term_delivery_1013.md | 0%
6 | 亮度合适、停转不伤眼 | 显示优化 | ✅ 达成当前期目标 | KR6.1 | 停转自动低亮 (1=有) | 是/否 | 越大越好 | 1 | 2026-10-12 | V0 2047 | 1 | 1 | 1 | ✅ | dr1v90 3bc5736 | 100%
7 | 长时间稳定 | 稳定 | 🔄 进行中 / 未达标 | KR7.1 | 丢帧/迟到率 | % | 越小越好 | 0 | 2026-10-13 | V0 2047 | 0.1 | 0.1 | 0.1 | ✅ | dr1v90 596b191 | 100%
|  |  |  | KR7.2 | 连续无故障: 软件链路 (假转, 无人值守) | h | 越大越好 | 0.17 | 2026-10-13 | V0 2047 | 8 | 8 | 24 | 🔄 | dr1v90 596b191 | 0.7083%
|  |  |  | KR7.3 | 连续无故障: 整机实转 (有人值守) | h | 越大越好 |  |  |  | 1 | 1 | 1 | ⏸
8 | 上电即用 | 运维 | 🔄 进行中 / 未达标 | KR8.1 | 上电到 0° 片亮起 (停转) | s | 越小越好 |  |  |  | 10 | 10 | 10 | ⏸
|  |  |  | KR8.4 | 上电到转稳全亮 | s | 越小越好 | 26 | 2026-10-12 | V0 2047 |  |  |  | 🔄 | claude_memory/project_slice_3bit_cpu_trial.md
|  |  |  | KR8.2 | 按名字找到板子 | s | 越小越好 | 34 | 2026-10-13 | V0 2047 | 20 | 20 | 20 | 🔄 | dr1v90 b0f6b5d | 58.82%
|  |  |  | KR8.3 | 需要串口 (1=需要) | 是/否 | 越小越好 | 0 | 2026-10-12 | V0 2047 | 0 | 0 | 0 | ✅ | dr1v90 30d82f9 | 100%
9 | 转起来能看状态、能远程升级 | 运维 | 🔄 进行中 / 未达标 | KR9.1 | 转子遥测可用 (1=可用) | 是/否 | 越大越好 | 0 | 2026-10-13 | V0 2047 | 1 | 1 | 1 | 🔄 | dr1v90 task/rotor-ops 05c4231 | 0%
|  |  |  | KR9.2 | 远程升级失败自动回滚 (1=有) | 是/否 | 越大越好 | 0 | 2026-10-13 | V0 2047 | 1 | 1 | 1 | 🔄 | dr1v90 task/rotor-ops 05c4231 | 0%
10 | 能放更多内容 | 内容 | ✅ 达成当前期目标 | KR10.1 | 可实时播放内容数 | 个 | 越大越好 | 2 | 2026-10-13 | V0 2047 | 2 | 5 | 10 | ✅ | dr1v90 887491a (live_push/README.md) | 20%
|  |  |  | KR10.2 | 交互方式数 | 种 | 越大越好 | 1 | 2026-10-13 | V0 2047 | 1 | 2 | 2 | ✅ | dr1v90 live_push/README.md | 50%
图例
✅ | 达成当前期目标
🔄 | 进行中 / 未达标
⏸ | 无数据 / 未开始
❌ | 退步 / 阻塞

## 指标趋势
每个 KR 一张趋势图 (横轴日期；同一天多次实测取最后一条；虚线 = V0/V1/V2 目标；橙线 = 仿真/台架)
KR1.1 内容刷新率 (假转, 管线能力) (fps, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-05-15 | 1.94 |  | 2026-05-15 | 15 | 2026-05-15 | 12 | 2026-05-15 | 15
2026-07-28 | 9.89 |  | 2026-10-13 | 15 | 2026-10-13 | 12 | 2026-10-13 | 15
2026-08-05 | 10.7
2026-08-06 | 15
2026-08-25 | 11
2026-10-12 | 15
2026-10-13 | 15
KR1.2 端到端延迟 p50 (ms, 越小越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 | 95 |  | 2026-10-12 | 100 | 2026-10-12 | 70 | 2026-10-12 | 70
|  |  | 2026-10-14 | 100 | 2026-10-14 | 70 | 2026-10-14 | 70
KR1.7 端到端延迟抖动 p99 (ms, 越小越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 | 236.6 |  | 2026-10-12 | 250 | 2026-10-12 | 120 | 2026-10-12 | 120
|  |  | 2026-10-14 | 250 | 2026-10-14 | 120 | 2026-10-14 | 120
KR1.3 WiFi 可用带宽 (Mbit/s, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-05-15 | 2.02 |  | 2026-05-15 | 10 | 2026-05-15 | 62 | 2026-05-15 | 62
2026-08-04 | 125 |  | 2026-10-12 | 10 | 2026-10-12 | 62 | 2026-10-12 | 62
2026-09-14 | 64.3
2026-09-15 | 136
2026-10-12 | 160
KR1.4 主机出帧耗时 p99 (ms, 越小越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-12 | 161 |  | 2026-10-12 | 50 | 2026-10-12 | 50 | 2026-10-12 | 50
2026-10-13 | 22 |  | 2026-10-13 | 50 | 2026-10-13 | 50 | 2026-10-13 | 50
KR1.5 板上切片耗时 (每帧) (ms, 越小越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标
2026-10-12 | 35 |  | 2026-10-12 | 55
2026-10-13 | 17.3 |  | 2026-10-13 | 55
KR1.6 内容刷新率 (实转上屏) (fps, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-12 | 10.8 |  | 2026-10-11 | 10.8 | 2026-10-11 | 12 | 2026-10-11 | 15
|  |  | 2026-10-13 | 10.8 | 2026-10-13 | 12 | 2026-10-13 | 15
KR2.1 体帧率 (Hz, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-08-04 | 22.1 |  | 2026-08-04 | 21.7 | 2026-08-04 | 24 | 2026-08-04 | 30
2026-10-12 | 21.7 |  | 2026-10-13 | 21.7 | 2026-10-13 | 24 | 2026-10-13 | 30
2026-10-13 |  | 24
KR3.1 每面像素数 (px, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-12 | 28800 |  | 2026-10-12 | 28800 | 2026-10-12 | 28800 | 2026-10-12 | 41472
2026-10-13 |  | 28800 | 2026-10-13 | 28800 | 2026-10-13 | 28800 | 2026-10-13 | 41472
KR3.2 每圈片数 (片, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-07-28 | 360 |  | 2026-07-28 | 142 | 2026-07-28 | 358 | 2026-07-28 | 605
2026-08-26 | 142 |  | 2026-10-13 | 142 | 2026-10-13 | 358 | 2026-10-13 | 605
2026-10-12 | 142
2026-10-13 |  | 358
KR4.1 色深 (bit/通道, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-07-28 | 1 |  | 2026-07-28 | 3 | 2026-07-28 | 12 | 2026-07-28 | 12
2026-08-20 | 3 |  | 2026-10-13 | 3 | 2026-10-13 | 12 | 2026-10-13 | 12
2026-09-02 |  | 12
2026-10-12 | 3
2026-10-13 |  | 12
KR4.2 链路色深 12-bit 已验证 (1=是) (是/否, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 |  | 1 | 2026-10-12 | 1 | 2026-10-12 | 1 | 2026-10-12 | 1
|  |  | 2026-10-14 | 1 | 2026-10-14 | 1 | 2026-10-14 | 1
KR5.1 几何 LUT 复现正确 (1=逐字节复现) (是/否, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-08-04 | 1 |  | 2026-08-04 | 1 | 2026-08-04 | 1 | 2026-08-04 | 1
2026-10-13 | 1 |  | 2026-10-13 | 1 | 2026-10-13 | 1 | 2026-10-13 | 1
KR5.2 左右镜像已核实 (1=已核) (是/否, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 | 0 |  | 2026-10-12 | 1 | 2026-10-12 | 1 | 2026-10-12 | 1
|  |  | 2026-10-14 | 1 | 2026-10-14 | 1 | 2026-10-14 | 1
KR6.1 停转自动低亮 (1=有) (是/否, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-12 | 1 |  | 2026-10-11 | 1 | 2026-10-11 | 1 | 2026-10-11 | 1
|  |  | 2026-10-13 | 1 | 2026-10-13 | 1 | 2026-10-13 | 1
KR7.1 丢帧/迟到率 (%, 越小越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 | 0 | 0 | 2026-10-12 | 0.1 | 2026-10-12 | 0.1 | 2026-10-12 | 0.1
|  |  | 2026-10-14 | 0.1 | 2026-10-14 | 0.1 | 2026-10-14 | 0.1
KR7.2 连续无故障: 软件链路 (假转, 无人值守) (h, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-12 |  | 47.9 | 2026-10-12 | 8 | 2026-10-12 | 8 | 2026-10-12 | 24
2026-10-13 | 0.17 |  | 2026-10-13 | 8 | 2026-10-13 | 8 | 2026-10-13 | 24
KR8.4 上电到转稳全亮 (s, 越小越好)
日期 | 实测 | 仿真/台架
2026-10-12 | 26
KR8.2 按名字找到板子 (s, 越小越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 | 34 |  | 2026-10-12 | 20 | 2026-10-12 | 20 | 2026-10-12 | 20
|  |  | 2026-10-14 | 20 | 2026-10-14 | 20 | 2026-10-14 | 20
KR8.3 需要串口 (1=需要) (是/否, 越小越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-12 | 0 |  | 2026-10-11 | 0 | 2026-10-11 | 0 | 2026-10-11 | 0
|  |  | 2026-10-13 | 0 | 2026-10-13 | 0 | 2026-10-13 | 0
KR9.1 转子遥测可用 (1=可用) (是/否, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 | 0 |  | 2026-10-12 | 1 | 2026-10-12 | 1 | 2026-10-12 | 1
|  |  | 2026-10-14 | 1 | 2026-10-14 | 1 | 2026-10-14 | 1
KR9.2 远程升级失败自动回滚 (1=有) (是/否, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 | 0 |  | 2026-10-12 | 1 | 2026-10-12 | 1 | 2026-10-12 | 1
|  |  | 2026-10-14 | 1 | 2026-10-14 | 1 | 2026-10-14 | 1
KR10.1 可实时播放内容数 (个, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 | 2 |  | 2026-10-12 | 2 | 2026-10-12 | 5 | 2026-10-12 | 10
|  |  | 2026-10-14 | 2 | 2026-10-14 | 5 | 2026-10-14 | 10
KR10.2 交互方式数 (种, 越大越好)
日期 | 实测 | 仿真/台架 | V0 目标 日期 | V0 目标 | V1 目标 日期 | V1 目标 | V2 目标 日期 | V2 目标
2026-10-13 | 1 |  | 2026-10-12 | 1 | 2026-10-12 | 2 | 2026-10-12 | 2
|  |  | 2026-10-14 | 1 | 2026-10-14 | 2 | 2026-10-14 | 2

## 燃起图
燃起图：总范围 / 按计划日期累计 / 实际完成累计 (今天之后不画完成线)
日期 | 总范围 | 计划累计 | 完成累计
2026-10-12 | 19 | 5 | 5
2026-10-13 | 19 | 7 | 10
2026-10-14 | 19 | 8
2026-10-15 | 19 | 9
2026-10-16 | 19 | 12
2026-10-17 | 19 | 14
2026-10-18 | 19 | 14
2026-10-19 | 19 | 14
2026-10-20 | 19 | 15
2026-10-21 | 19 | 15
2026-10-22 | 19 | 17
2026-10-23 | 19 | 17
2026-10-24 | 19 | 18
交付清单
id | 名称 | 服务的 goal_id | 期 | 计划日期 | 完成日期 | 状态 | 分支/提交
E1 | ARM 主控 WiFi 点对点实测 ≥160 Mbit/s | 1 | 公共 | 2026-10-12 | 2026-10-12 | ✅ | ~/pov_work/wifibw/2026-10-12_p2p (project_m90_wifi_p2p_1012)
E2 | 3-bit 屏 CPU 板上切片上屏 | 1;3 | 公共 | 2026-10-12 | 2026-10-12 | ✅ | dr1v90 6ead419
E3 | 开机自动演示 + 转速门控 | 8;10 | 公共 | 2026-10-12 | 2026-10-12 | ✅ | dr1v90 3bc5736
E4 | 停转低亮 0° 片 | 6 | 公共 | 2026-10-12 | 2026-10-12 | ✅ | dr1v90 3bc5736 (7a8c402)
E5 | 开机自连 WiFi | 8;9 | 公共 | 2026-10-12 | 2026-10-12 | ✅ | dr1v90 30d82f9
E6 | 按名字找板 (mDNS) | 8;9 | 公共 | 2026-10-13 | 2026-10-13 | ✅ | dr1v90 b0f6b5d
E7 | 纯切片 30 Hz 位流上硅 D'0–D'3 | 2;3 | 公共 | 2026-10-13 | 2026-10-13 | ✅ | dr1v90 71d006f / 473abcf
D1 | 主机实时推流 | 1;10 | 公共 | 2026-10-14 | 2026-10-13 | ✅ | task/live-push-2047 → 主线 9bf16ad
D2 | 2047 PL 切片实时片流 | 1;2;3 | 公共 | 2026-10-16 |  | 🔄 | task/pls-2047 (fb89d07)
D3 | 上行出口 12-bit (2 期加 1.2G) | 2;3;4 | 2260 | 2026-10-16 |  | 🔄 | task/ul-fmt-30hz (7164f44)
D4 | 桥侧接收核对 12-bit | 2;4 | 2260 | 2026-10-16 |  | 🔄 | task/bridge-c1 (7a1a17f)
D5 | 桥驱动 2260 1 期 6 链 24 Hz 12-bit | 2;3;4 | 2260 | 2026-10-17 | 2026-10-13 | ✅ | task/bridge-2260-p1 → 主线 cdf49c6
D6 | 几何 LUT + 转起来校准 | 5 | 公共 | 2026-10-15 | 2026-10-13 | ✅ | task/geo-lut-p1 → 主线 44ed2cd；改 358 片 a9fc48c
D7 | 转子运维 (netguard-lite / 遥测 / 远程升级) | 7;9 | 公共 | 2026-10-17 |  | 🔄 | task/rotor-ops (05c4231，返工中)
D8 | 主控↔桥联合仿真 | 2;4;7 | 2260 | 2026-10-20 |  | ⏸ | 待派 (D3+D4+D5 后)
D9 | 全链路系统仿真 (主机→2260 模型) | 1;2;7 | 2260 | 2026-10-22 |  | ⏸ | 待派
D10 | 1 期主控整合位流 | 2;3 | 2260 | 2026-10-22 |  | ⏸ | 待派
D11 | C1 台架彩排 + 1.2G 误码测试 | 2;4;7 | 2260 | 2026-10-24 |  | ⏸ | 待派 (需用户接线一次)
B1 | 启动阶段屏显 (停转 0° 片当平面屏: ①PL 静态 logo ②启动状态逐行显示, 走公共片流 ③转稳切正常内容) | 8;9 | 公共 |  |  | ⏸ backlog 未派 | 用户 10-13 定只记录; 与 D7 最近

## 里程碑趋势
里程碑趋势图 MTA：横轴评审日期，纵轴预计完成日期；线往上翘 = 延期，水平 = 按期；灰色对角线 = 评审日期本身 (碰到即完成)
评审日期 | V0 公共部分完成 | 1 期链路离线全通 | C1 台架彩排 | 验证板 PCB 回板 | 1 期点亮出图 | 1 期转起来 24 Hz | 对角线
2026-10-13 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-11-10 | 2026-11-12 | 2026-11-17
对角线 (y = x)
2026-10-13 | 2026-10-13
2026-11-17 | 2026-11-17

## 历史记录
日期 | goal_id | kr_id | 指标 | 单位 | 实测值 | 硬件/阶段 | 来源 | 备注
2026-05-15 | 1 | KR1.1 | 内容刷新率 (假转, 管线能力) | fps | 1.94 | 历史 Zynq7020 | claude_memory/feedback_30fps_progress_log.md | 1-bit；ESP32 SDIO WiFi 桥；端到端推流均值
2026-05-15 | 1 | KR1.3 | WiFi 可用带宽 | Mbit/s | 2.02 | 历史 Zynq7020 | claude_memory/feedback_30fps_progress_log.md | ESP32 SDIO 桥；办公网 198 s 持续均值
2026-07-28 | 1 | KR1.1 | 内容刷新率 (假转, 管线能力) | fps | 9.89 | 历史 Zynq7020 | claude_memory/reference_pov_wifi_streaming.md | PVS1 推流 (1-bit 360 片 zlib)
2026-07-28 | 3 | KR3.2 | 每圈片数 | 片 | 360 | 历史 Zynq7020 | claude_memory/reference_pov_wifi_streaming.md | 1-bit 360 片 (超出面板真实能力)
2026-07-28 | 4 | KR4.1 | 色深 | bit/通道 | 1 | 历史 Zynq7020 | claude_memory/reference_pov_wifi_streaming.md | 1-bit
2026-08-04 | 1 | KR1.3 | WiFi 可用带宽 | Mbit/s | 125 | 历史 Zynq7020 | claude_memory/feedback_wifi_throughput_bottleneck_isolated.md | MT7921AU USB；停掉看门狗后 23→58→打到极限 ~125
2026-08-04 | 2 | KR2.1 | 体帧率 | Hz | 22.1 | 历史 Zynq7020 | claude_memory/reference_pov3d_brightness_control_limits.md | 真机 663 RPM locked=1
2026-08-04 | 5 | KR5.1 | 几何 LUT 复现正确 (1=逐字节复现) | 是/否 | 1 | 历史 Zynq7020 | claude_memory/reference_pov3d_brightness_control_limits.md | v3.1 偏心几何真机目视成立
2026-08-05 | 1 | KR1.1 | 内容刷新率 (假转, 管线能力) | fps | 10.7 | 历史 Zynq7020 | claude_memory/feedback_lz4_onboard_reality_check.md | lz4 上板 10.0–11.4 取中；假转 16.1 rps
2026-08-06 | 1 | KR1.1 | 内容刷新率 (假转, 管线能力) | fps | 15 | 历史 Zynq7020 | claude_memory/feedback_recv_setsockopt_rcvbuf_lock.md (mlkpai_fs03 7e7773e) | 去掉 SO_RCVBUF 锁后 flip 中位 15.00/s；900 RPM 口径
2026-08-20 | 4 | KR4.1 | 色深 | bit/通道 | 3 | 历史 Zynq7020 | claude_memory/project_pov3d_3bit_color.md | 行内 BCM 3-bit 上板
2026-08-25 | 1 | KR1.1 | 内容刷新率 (假转, 管线能力) | fps | 11 | 历史 Zynq7020 | claude_memory/project_pov3d_3bit_color.md | 改 3-bit 后 PL 三引擎解码 + fold_a：969 RPM 下 10–12 fps
2026-08-26 | 3 | KR3.2 | 每圈片数 | 片 | 142 | 历史 Zynq7020 | claude_memory/project_pov3d_nslices_match_panel.md | n_slices 匹配面板真实能力 → 142 槽/面
2026-09-02 | 4 | KR4.1 | 色深 | bit/通道 | 12 | 台架 | claude_memory/project_icnd2260_working_config_2026_09_02.md | 单颗 2260 台架 11000 fps 下色深 12.0 位 (推断)
2026-09-14 | 1 | KR1.3 | WiFi 可用带宽 | Mbit/s | 64.3 | 历史 DR1V90 | claude_memory/reference_dr1_wifi_ceiling_unestablished.md (dr1v90 measure/03_wifibw/results/2026-09-14) | RISC-V 办公网 iperf3 正向中位；单核 CPU 打满
2026-09-15 | 1 | KR1.3 | WiFi 可用带宽 | Mbit/s | 91.7 | 历史 DR1V90 | claude_memory/reference_dr1_wifi_ceiling_unestablished.md | 点对点台架 原版
2026-09-15 | 1 | KR1.3 | WiFi 可用带宽 | Mbit/s | 136 | 历史 DR1V90 | claude_memory/reference_dr1_wifi_ceiling_unestablished.md | 点对点台架 v3p1 + USB RX 聚合
2026-10-12 | 1 | KR1.1 | 内容刷新率 (假转, 管线能力) | fps | 12.5 | V0 2047 | claude_memory/project_slice_3bit_cpu_trial.md | DR1M90 板上 CPU 切片 voxslice 0.1 (12–13 fps；切片打满 CPU1)
2026-10-12 | 1 | KR1.1 | 内容刷新率 (假转, 管线能力) | fps | 15 | V0 2047 | dr1v90 dddf19a | voxslice 0.2 bonsai 稳 15 fps (假转 16.15 rps)
2026-10-12 | 1 | KR1.3 | WiFi 可用带宽 | Mbit/s | 160 | V0 2047 | claude_memory/project_m90_wifi_p2p_1012.md | ARM DR1M90 点对点 TCP 推流方向 ≥160 (台架封顶，CPU 未满)
2026-10-12 | 1 | KR1.4 | 主机出帧耗时 p99 | ms | 161 | V0 2047 | dr1v90 live_push/README.md (anim_vox 原离线路径) | 原算法单帧 155–167 ms 取中
2026-10-12 | 1 | KR1.5 | 板上切片耗时 (每帧) | ms | 80 | V0 2047 | claude_memory/project_slice_3bit_cpu_trial.md (dr1v90 887c831) | voxslice 0.1 bonsai 78–82 ms
2026-10-12 | 1 | KR1.5 | 板上切片耗时 (每帧) | ms | 35 | V0 2047 | dr1v90 dddf19a | voxslice 0.2 bonsai 34–36 ms (紧凑列存 + 双核分片)
2026-10-12 | 1 | KR1.6 | 内容刷新率 (实转上屏) | fps | 10.8 | V0 2047 | claude_memory/project_slice_3bit_cpu_trial.md (D9 首次转起来 640–654 RPM) | 由实转 ~650 RPM 推算 (= rps), 非逐帧计数
2026-10-12 | 2 | KR2.1 | 体帧率 | Hz | 21.7 | V0 2047 | claude_memory/project_slice_3bit_cpu_trial.md | D9 DR1M90 首次转起来 640–654 RPM
2026-10-12 | 3 | KR3.1 | 每面像素数 | px | 28800 | V0 2047 | claude_memory/project_slice_3bit_cpu_trial.md | ICND2047 160×180
2026-10-12 | 3 | KR3.2 | 每圈片数 | 片 | 142 | V0 2047 | claude_memory/project_slice_3bit_cpu_trial.md | DR1M90 双面各 142 槽
2026-10-12 | 4 | KR4.1 | 色深 | bit/通道 | 3 | V0 2047 | claude_memory/project_slice_3bit_cpu_trial.md | DR1M90 3-bit
2026-10-12 | 6 | KR6.1 | 停转自动低亮 (1=有) | 是/否 | 1 | V0 2047 | dr1v90 3bc5736 | 停转低亮 0° 片上板通过并固化；4 次起停无 FAULT
2026-10-12 | 7 | KR7.2 | 连续无故障: 软件链路 (假转, 无人值守) | h | 47.9 | 台架 | claude_memory/project_lane47_soak_verdict_1012.md | 仅上行链路长跑 1.56e9 帧 0 错
2026-10-12 | 8 | KR8.3 | 需要串口 (1=需要) | 是/否 | 0 | V0 2047 | dr1v90 30d82f9 | 开机自连 WiFi 重启实测通过，用户拔掉串口
2026-10-12 | 8 | KR8.4 | 上电到转稳全亮 | s | 26 | V0 2047 | claude_memory/project_slice_3bit_cpu_trial.md | 重启后 uptime 26 s 转速门控亮起播 walking
2026-10-13 | 1 | KR1.1 | 内容刷新率 (假转, 管线能力) | fps | 15 | V0 2047 | dr1v90 596b191 / 9bf16ad | 主机实时推流 10 min：rx/切片/翻页 15.0 fps
2026-10-13 | 1 | KR1.2 | 端到端延迟 p50 | ms | 114 | V0 2047 | dr1v90 60c619a (live_push/README.md) | 第一次上板：停等发送 + --max-fps 15，未过
2026-10-13 | 1 | KR1.2 | 端到端延迟 p50 | ms | 84.7 | V0 2047 | dr1v90 596b191 | 发送流水线 + --max-fps 0；p95 158 / p99 198 ms
2026-10-13 | 1 | KR1.2 | 端到端延迟 p50 | ms | 95 | V0 2047 | dr1v90 9bf16ad | 主会话新克隆独立复验
2026-10-13 | 1 | KR1.4 | 主机出帧耗时 p99 | ms | 23 | V0 2047 | dr1v90 887491a | voxlive 实时路径单帧 ~23 ms
2026-10-13 | 1 | KR1.4 | 主机出帧耗时 p99 | ms | 20.3 | V0 2047 | dr1v90 596b191 | 10 min 连续出帧 p99 18.7–20.3 ms
2026-10-13 | 1 | KR1.4 | 主机出帧耗时 p99 | ms | 22 | V0 2047 | dr1v90 9bf16ad | 主会话独立复验 p99 22 ms
2026-10-13 | 1 | KR1.5 | 板上切片耗时 (每帧) | ms | 17.3 | V0 2047 | dr1v90 596b191 | groot 实时推流 (体素比 bonsai 少，内容不同)
2026-10-13 | 1 | KR1.7 | 端到端延迟抖动 p99 | ms | 198 | V0 2047 | dr1v90 596b191 | agent 上板实测 p99
2026-10-13 | 1 | KR1.7 | 端到端延迟抖动 p99 | ms | 236.6 | V0 2047 | dr1v90 9bf16ad | 主会话新克隆独立复验 p99 (9381 帧)
2026-10-13 | 10 | KR10.1 | 可实时播放内容数 | 个 | 2 | V0 2047 | dr1v90 887491a (live_push/README.md) | walking / groot 实时推流逐字节核过
2026-10-13 | 10 | KR10.2 | 交互方式数 | 种 | 1 | V0 2047 | dr1v90 live_push/README.md | --keys 键盘旋转/缩放
2026-10-13 | 2 | KR2.1 | 体帧率 | Hz | 30 | 台架 | dr1v90 71d006f | 30 Hz 纯切片位流第一次上硅 (无屏)：切片链按 30 Hz 节拍跑通，尾部 late 0.2%
2026-10-13 | 2 | KR2.1 | 体帧率 | Hz | 24 | 仿真 | dr1v90 cdf49c6 | 1 期桥 6 链 1串2 4296 片/s = 24 Hz×358 片 (余量 0.40%)
2026-10-13 | 3 | KR3.1 | 每面像素数 | px | 28800 | 仿真 | dr1v90 cdf49c6 | 1 期 2260 验证板 160×180
2026-10-13 | 3 | KR3.2 | 每圈片数 | 片 | 358 | 仿真 | dr1v90 a9fc48c / cdf49c6 | 1 期 LUT 358 片 + 桥仿真
2026-10-13 | 4 | KR4.1 | 色深 | bit/通道 | 12 | 仿真 | dr1v90 cdf49c6 | 1 期桥 12-bit 整链仿真 PASS
2026-10-13 | 4 | KR4.2 | 链路色深 12-bit 已验证 (1=是) | 是/否 | 1 | 仿真 | dr1v90 cdf49c6 (gw5a_bridge/p1 verify ALL PASS) | 仅桥→2260 段仿真; 主控→桥→2260 全链未验
2026-10-13 | 5 | KR5.1 | 几何 LUT 复现正确 (1=逐字节复现) | 是/否 | 1 | V0 2047 | dr1v90 44ed2cd | 几何 LUT 生成器逐字节复现 2047 s3lut，verify 22 PASS
2026-10-13 | 5 | KR5.2 | 左右镜像已核实 (1=已核) | 是/否 | 0 | V0 2047 | claude_memory/project_short_term_delivery_1013.md | 2047 是否整体左右镜像未核
2026-10-13 | 7 | KR7.1 | 丢帧/迟到率 | % | 0.2 | 台架 | dr1v90 71d006f | 纯切片 30 Hz 硅上尾部 late 0.2%
2026-10-13 | 7 | KR7.1 | 丢帧/迟到率 | % | 0 | 台架 | dr1v90 473abcf | 暂停 netguard 后 late/miss 0 (10 s 一阵 late 来自 netguard)
2026-10-13 | 7 | KR7.1 | 丢帧/迟到率 | % | 0 | V0 2047 | dr1v90 596b191 | 实时推流 624 s NAK 0 / forced 0
2026-10-13 | 7 | KR7.2 | 连续无故障: 软件链路 (假转, 无人值守) | h | 0.17 | V0 2047 | dr1v90 596b191 | 实时推流连续 624 s 无故障 (未做更长)
2026-10-13 | 8 | KR8.2 | 按名字找到板子 | s | 34 | V0 2047 | dr1v90 b0f6b5d | 无串口自重启后 34 s 按名字找到并 ssh 上
2026-10-13 | 9 | KR9.1 | 转子遥测可用 (1=可用) | 是/否 | 0 | V0 2047 | dr1v90 task/rotor-ops 05c4231 | D7 返工中 (首次复验 T5 偶发 FAIL)
2026-10-13 | 9 | KR9.2 | 远程升级失败自动回滚 (1=有) | 是/否 | 0 | V0 2047 | dr1v90 task/rotor-ops 05c4231 | D7 返工中